Temporal Graph Foundation Model

Project Plan — Cross-domain pretraining on art, prediction markets, and energy

Bloomsbury Technology · April 2026

# Summary

Bloomsbury Technology holds roughly $100K in unspent compute credits from a partner, fifteen interns available over the summer, and three proprietary temporal graph datasets — art market auctions (893K lots), Polymarket prediction markets (11K resolved markets, 14.8M trades), and partner-supplied energy trading data. This plan proposes spending those resources to pretrain a temporal heterogeneous Bayesian graph foundation model on the merged dataset, with Arina's BTHGNN architecture as the starting point and domain-specific fine-tuned heads as the downstream deliverables.

# Why this project, why now

## What's on the table

- Compute. ~$100K in partner credits that currently have no allocated use. Pretraining a graph foundation model is one of the few research activities that actually consumes that scale of compute productively.

- Data. Three heterogeneous temporal graph datasets that almost no other academic group has. Most GFM work trains on OGB or Wikipedia-derived graphs; we have real-world transactional data with resolved ground truth.

- People. Fifteen interns arriving over the summer, plus Arina already working on the temporal Bayesian GNN architecture that this project is built around.

- Temporal edge. Most graph foundation models published so far treat graphs as static snapshots. Temporal structure is where the real signal lives in all three of our domains — and it's where the GFM literature is thinnest. This is a publishable contribution on its own, not just an engineering detail.

## Why it's worth doing over the alternatives

The alternative uses for the compute are (a) let it expire unused, (b) run bigger versions of existing experiments, or (c) train domain-specific models that don't transfer. None of these produce a research artifact with the same leverage. A foundation model becomes the substrate for future BT research across every domain where we hold graph data — and it seeds the kind of methodological reputation that drives both NeurIPS acceptances and commercial conversations.

# Architecture

## Base model: temporal heterogeneous Bayesian GNN

The starting point is Arina's BTHGNN architecture, extended to handle cross-domain pretraining. The four design commitments:

- Heterogeneous. Explicit modelling of node types (artist, work, gallery, trader, market, generator, substation) and edge types (sale, trade, dispatch, provenance). Domain-specific embeddings project into a shared latent space for cross-domain learning.

- Temporal. Time-aware message passing, either via temporal graph transformers (Rossi et al. TGN lineage) or via recurrent updates on node states. Nodes and edges have activation windows; the model sees the graph as it was at time t, not the final static version.

- Bayesian. Posterior distributions over embeddings, not point estimates. This is what gives us calibrated uncertainty for downstream forecasting tasks and directly addresses the Foong/Folgoc critique of MC dropout (which Arina needs to handle anyway for BTHGNN).

- Foundation-model scale. Enough capacity to benefit from the compute budget — probably on the order of 100M–500M parameters, depending on whether we're compute-bound or data-bound. Exact size locked in Phase 0.

## Training objectives

Pretraining loss is a weighted sum of four self-supervised objectives, with weights tuned per phase:

- Masked node attribute prediction. Mask out node features, predict from neighbourhood. Teaches the model to use graph structure for node understanding.

- Temporal link prediction. Given the graph up to time t, predict which edges appear at time t+1. Teaches temporal dynamics.

- Subgraph contrastive learning. Positive pairs are temporally adjacent subgraphs from the same domain; negatives are random subgraphs. Learns domain structure.

- Cross-domain contrastive alignment. Positive pairs are structurally analogous subgraphs across domains (a trader-market bipartite cluster vs an artist-gallery cluster); negatives are within-domain. This is the objective that actually forces cross-domain transfer and is the main scientific question of the project.

# Data

Three domains, each needing different amounts of work to reach training-ready state:

| Domain | Have now | Need to gather | Effort |
| --- | --- | --- | --- |
| Art market | 893K lots across 3 houses; artist/medium/price/provenance in ClickHouse | Artist metadata timelines, gallery histories, exhibition graphs, dealer–collector edges | High: 4–5 interns, 3–4 weeks scraping + curation |
| Polymarket | 11K resolved markets, 14.8M trades, full order books; wallet & trade graphs reconstructable | Trader clustering, cross-market portfolios, temporal snapshots beyond the current 6-day window | Medium: 2–3 interns; mostly SQL and feature engineering |
| Energy | Trading data from partner (scope TBD) | Confirm whether data includes dispatch/load pairings or only prices; grid topology; temporal resolution | Unknown until partner data is audited |

Unified schema. All three domains are normalised to a common temporal graph format: typed nodes with attribute vectors, typed edges with timestamps and validity windows, domain tag as a node attribute. The ingest pipeline is the single largest engineering task in Phase 1 and is the natural place to put interns with SQL and data engineering skills.

Temporal alignment. Art trades are sparse (irregular sale dates), Polymarket is dense (every trade timestamped to the second), energy is regular (hourly or sub-hourly). The schema stores raw timestamps; the training pipeline resamples to a common cadence per task, with careful forward-fill rules for sparse domains documented up front so we don't lose signal by over-smoothing.

# Team and resourcing

## Leads

- Arina Redina — technical lead. BTHGNN architecture is her work; extending it to multi-domain pretraining is the natural next step. This replaces her BTHGNN autumn track rather than adding to it.

- Maxim Kalpin — infrastructure lead. ClickHouse pipelines, training infrastructure, compute orchestration. Already on γ and δ in the ICML sprint; this project absorbs both.

- Eugene — scientific direction and writing. Objectives, evaluation design, paper lead. Light compared to the May sprint load.

## Interns (fifteen)

- Data team (8). Split across the three domains per the table above. Most work is scraping, curation, schema normalisation, and validation. Clear, well-scoped tasks with visible outputs — good intern work.

- Modeling team (4). Ablations, baselines, evaluation harnesses. Supervised by Arina and Maxim.

- Analysis team (3). Downstream evaluations, interpretability probes, paper figures.

# Timeline

| Phase | Window | Deliverables | Gate |
| --- | --- | --- | --- |
| 0. Scoping | Apr 13–20 | Audit energy data with partner; confirm art graph schema; lock Arina's BTHGNN architecture as the base; write 10-page design doc | Go/no-go decision Apr 20 |
| 1. Data | Apr 20 – May 18 | Intern teams gather domain-specific enrichment; build unified temporal graph schema; ingest into ClickHouse/parquet; temporal alignment pipeline | Unified dataset v0 by May 18 |
| 2. Pretrain | May 18 – Jun 22 | Pretraining on merged graph: masked node/edge prediction, temporal link prediction, contrastive cross-domain objectives; ablations on held-out domain | Loss curves flat, cross-domain probes beat single-domain baselines |
| 3. Fine-tune | Jun 22 – Jul 20 | Domain heads: art price forecasting, Polymarket resolution, energy load forecasting; benchmark vs domain-specific baselines | Beat domain-specific baselines on ≥2 of 3 domains |
| 4. Write | Jul 20 – Aug 22 | Main paper (NeurIPS main track or workshop); domain application papers; arXiv preprint; dataset release | NeurIPS workshop deadlines ~mid-Sep |

Critical gates. The Apr 20 scoping gate is the most important — if the energy data doesn't support temporal graph construction, the project is two domains not three, and the design changes. The May 18 unified-dataset gate is when we know whether the data engineering is tractable. The late-June pretrain gate is where we find out whether cross-domain transfer actually happens; if it doesn't, we still have three domain-specific temporal GNNs, which is still three papers.

# Interaction with the May ICML sprint

This project reshapes the May sprint portfolio rather than competing with it:

- γ (Graph FM for art markets) drops from the May sprint. The April 24 deadline becomes untenable if we're building our own GFM; applying off-the-shelf GFMs to art market data is no longer the interesting paper once we're training our own. γ returns in autumn as GFM-3, substantially stronger.

- α stays but narrows. For May, α is the feature-leakage and Orth-SVAE interpretability paper on Polymarket — a tight, well-scoped hypothesis-testing paper. In autumn, GFM-2 becomes the broader interpretability story using GFM embeddings.

- δ (POLYBENCH) stays. In fact the benchmark becomes more valuable because we'll use it ourselves to evaluate the GFM.

- Ω, ε, π, RL, β are unaffected. These are dissertation-derived or domain-specific and don't overlap with the GFM track.

Net effect on the May sprint: one paper drops from the portfolio (γ), easing the April 24 crunch substantially. The Eugene bottleneck eases correspondingly. Arina's May load drops because BTHGNN is no longer a separate autumn track — it's this project, starting now.

# Paper outputs

| Code | Paper | Target venue | Timing |
| --- | --- | --- | --- |
| GFM-0 | Temporal heterogeneous Bayesian GFM: methods paper | NeurIPS main track (or GFM workshop as fallback) | Sep 2026 |
| GFM-1 | Cross-domain transfer: what transfers and why | NeurIPS workshops (GFM, Temporal Graphs) | Sep 2026 |
| GFM-2 | Polymarket application: interpretability via GFM embeddings (subsumes earlier α) | ICLR 2027 or NeurIPS workshop | Oct 2026 |
| GFM-3 | Art market application: valuation and market dynamics (subsumes earlier γ and β) | ICLR 2027 or domain venue | Oct 2026 |

Four papers out of one research artifact, staggered across NeurIPS 2026 workshops and ICLR 2027. The main methods paper is the headline contribution; the three application papers build on the same trained model and demonstrate its value across domains. A dataset release (the unified temporal graph) is a separate deliverable that accompanies the methods paper and drives citations.

# Open decisions

Four questions need answers before the project can be committed, all resolvable in the Phase 0 scoping window:

- Does the energy data actually support temporal graph construction? Audit required with the partner. Without this, the project is two domains, not three, and the cross-domain story weakens.

- Is Arina bought into leading this? This replaces her BTHGNN plan with something larger and more ambitious. If she'd rather ship BTHGNN as a focused paper, the plan changes.

- What's the right model size for the compute budget? Decision depends on data scale — compute-bound or data-bound. Rough calculation in Phase 0.

- NeurIPS main track or workshop as the target? Main track is more ambitious and later (May 2027 cycle); NeurIPS workshops are September 2026 and give us a timed milestone. The plan defaults to workshops, with main-track resubmission as an option after workshop feedback.

# Recommendation

Commit to the Phase 0 scoping window: ten days (April 13–20) to audit the energy data, confirm Arina's buy-in, and write the detailed design document. Lock the full project on April 20 conditional on the scoping gate passing. Drop γ from the May sprint immediately to relieve the April 24 crunch.

— Draft plan, prepared for Eugene, April 2026